|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|

|  |  |  |
| --- | --- | --- |
|

|  |  |
| --- | --- |
|

|  |
| --- |
| WEEKLY UPDATE 12th August 2019: Meat Industry Strategic Plan 2030  |

 |

 |

|  |  |
| --- | --- |
|

|  |
| --- |
|  |

 |

 |
|

|  |  |  |
| --- | --- | --- |
|

|  |  |
| --- | --- |
|

|  |
| --- |
| Hi everyone, **Project status**MISP has now completely entered drafting phase in the lead up to October 2019 finalisation. A project report can be found [here](https://rmac.us17.list-manage.com/track/click?u=23f496884edecf7b6f1c75452&id=6130dc9147&e=5bfb5f5a03). This week sees a critical project phase with all MISP partners meeting in Canberra 13 - 14 August. A reminder that Tamara Badenoch is the key liaison point on this project moving forward and can be contacted on [tamara@rmac.com.au](https://rmac.us17.list-manage.com/track/click?u=23f496884edecf7b6f1c75452&id=4ed619b7c1&e=5bfb5f5a03). **Last week (w/c 5th Aug)** * August CDT meeting (6 Aug) to review further MISP drafting
* Iteration of MISP based on CDT comment
* Development of next MISP iteration for RMAC review
* Preparation for RMAC meeting to review next MISP iteration
* Continued full MISP document drafting

 **Next week (w/c 12th Aug)** * Review of next MISP iteration with combined RMAC Board/CEO meeting
* Further iteration of MISP based on RMAC Board/CEO feedback
* Continued full MISP document drafting

**Drafting and Review Schedule**  Please be advised in this phase of the key drafting and review dates: * 5 August – Distribute Draft Strategy + Other Materials to CDT **[COMPLETE]**
* 6 August – CDT Review Session **[COMPLETE]**
* 9 Aug – Draft 1 released for Board + CEOs **[COMPLETE]**
* 13 – 14 August – Board + CEO page turn of Draft 1
* 19 August – 30 August – Next release – RMAC CEOs and Directors will be sharing with their boards and we have various stakeholder engagements locked in over this period.
* 23 August – FYI ONLY: RMAC Internal Planning Day
* 27 August – Distribution of materials for September CDT
* 29 August – FYI ONLY: Joint Partner Communications Planning Day
* 5 September – September CDT
* 9 September – Final Draft released
* 13 September – RMAC CEO and Board Strategy Final Review meeting
* 30 September – Proposed finalisation of Final Draft
* 16 October – Launch

This week will be a very busy one for RMAC so your patience as ever appreciated in receiving a response! Kind Regards, |

 |

 |

 |