|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| |  |  |  | | --- | --- | --- | | |  |  | | --- | --- | | |  | | --- | | WEEKLY UPDATE 12th August 2019: Meat Industry Strategic Plan 2030 | | |  |  |  | | --- | --- | | |  | | --- | |  | | |
| |  |  |  | | --- | --- | --- | | |  |  | | --- | --- | | |  | | --- | | Hi everyone,   **Project status** MISP has now completely entered drafting phase in the lead up to October 2019 finalisation. A project report can be found [here](https://rmac.us17.list-manage.com/track/click?u=23f496884edecf7b6f1c75452&id=6130dc9147&e=5bfb5f5a03). This week sees a critical project phase with all MISP partners meeting in Canberra 13 - 14 August.   A reminder that Tamara Badenoch is the key liaison point on this project moving forward and can be contacted on [tamara@rmac.com.au](https://rmac.us17.list-manage.com/track/click?u=23f496884edecf7b6f1c75452&id=4ed619b7c1&e=5bfb5f5a03).   **Last week (w/c 5th Aug)**   * August CDT meeting (6 Aug) to review further MISP drafting * Iteration of MISP based on CDT comment * Development of next MISP iteration for RMAC review * Preparation for RMAC meeting to review next MISP iteration * Continued full MISP document drafting     **Next week (w/c 12th Aug)**   * Review of next MISP iteration with combined RMAC Board/CEO meeting * Further iteration of MISP based on RMAC Board/CEO feedback * Continued full MISP document drafting   **Drafting and Review Schedule**    Please be advised in this phase of the key drafting and review dates:   * 5 August – Distribute Draft Strategy + Other Materials to CDT **[COMPLETE]** * 6 August – CDT Review Session **[COMPLETE]** * 9 Aug – Draft 1 released for Board + CEOs **[COMPLETE]** * 13 – 14 August – Board + CEO page turn of Draft 1 * 19 August – 30 August – Next release – RMAC CEOs and Directors will be sharing with their boards and we have various stakeholder engagements locked in over this period. * 23 August – FYI ONLY: RMAC Internal Planning Day * 27 August – Distribution of materials for September CDT * 29 August – FYI ONLY: Joint Partner Communications Planning Day * 5 September – September CDT * 9 September – Final Draft released * 13 September – RMAC CEO and Board Strategy Final Review meeting * 30 September – Proposed finalisation of Final Draft * 16 October – Launch   This week will be a very busy one for RMAC so your patience as ever appreciated in receiving a response!   Kind Regards, | | | |